GMTK GAME JAM 2026

Team Planning & Documentation

July 22–26, 2026  |  96 Hours  |  itch.io

# 1.  Jam Overview

| Detail | Info |
| --- | --- |
| Dates | July 22–26, 2026 (96 hours) |
| Theme | Revealed at jam start — TBA |
| Submit via | itch.io — Windows playable build required |
| Team size | No limit — we are a team of 2 |
| File size limit | 1 GB max on itch.io |
| Rating period | 5 days after jam ends — no updates allowed |

# 2.  Team

| Name | Role | Skills | Contact |
| --- | --- | --- | --- |
|  | Programmer | Python |  |
|  | Programmer / Art | Python |  |

# 3.  Engine Decision

Decide before July 22nd. Both members must have it installed and tested.

| Engine | Language | Game-Ready | Difficulty | Notes |
| --- | --- | --- | --- | --- |
| Pygame | Python | Yes | Low–Medium | Recommended — Python, game-focused |
| Godot | GDScript | Yes | Medium | Best results, Python-like syntax |
| Tkinter | Python | Limited | Low | Not ideal for games — avoid |

Our decision:  _______________________________________________

# 4.  Pre-Jam Checklist

Complete everything below before July 22nd.

## 4.1  Engine & Tools

☐  Decide on engine — both members agree

☐  Both install the engine and run a test project successfully

☐  Set up a shared GitHub repo

☐  Test that both can push and pull from the repo

☐  Agree on folder structure and file naming conventions

## 4.2  Communication

☐  Set up a Discord server or group chat for the jam

☐  Agree on working hours and scheduled break times

☐  Share phone numbers in case of internet issues

## 4.3  Assets

☐  Bookmark free asset sites (Kenney.nl, freesound.org, itch.io assets)

☐  Decide who handles art and who handles sound

☐  Download a generic Kenney asset pack in advance

☐  Pick and download a font from Google Fonts

## 4.4  Accounts & Registration

☐  Both have an itch.io account

☐  Decide who will submit the final game

☐  Register on the GMTK itch.io jam page to get the theme email

# 5.  Game Concept  (fill in on Day 1)

Spend at least 1 hour brainstorming before locking in a concept.

## 5.1  Theme & Brainstorm

Theme:  _______________________________________________

Initial ideas — write 5–10 before deciding:

## 5.2  Chosen Concept

| Field | Answer |
| --- | --- |
| Game Title |  |
| Genre | e.g. Platformer / Puzzle / Top-down / Arcade |
| Core Loop | What does the player do every 30 seconds? |
| Win / Lose Condition | How does the player win or lose? |
| Theme Tie-in | How does it connect to the jam theme? |

## 5.3  Scope — Must Have vs Nice to Have

Be ruthless. A small finished game beats a big unfinished one every time.

| ✅ Must Have (ship without these = not a game) | ⭐ Nice to Have (only if time allows) |
| --- | --- |

# 6.  96-Hour Jam Schedule

Suggested time breakdown — adjust as you go.

| Time | Focus |
| --- | --- |
| Hour 0–2 | Theme reveal — brainstorm ideas, vote on concept |
| Hour 2–4 | Lock in concept, assign tasks, set up project & repo |
| Hour 4–16 | Core mechanics — get something playable ASAP |
| Hour 16–24 | First playable build — identify what is actually fun |
| Hour 24–60 | Polish, art, sound, levels, bug fixing |
| Hour 60–88 | Final polish, playtesting, balancing |
| Hour 88–96 | Export build, write itch.io page, submit |

# 7.  During Jam Checklist

## Hour 0 — Theme Reveal

☐  Read the theme carefully — don’t rush into an idea

☐  Spend at least 1 hour brainstorming before committing

☐  Vote on the best idea together

☐  Fill in Section 5 above

☐  Set a milestone: what should be playable by Hour 16?

## Hour 2 — Setup

☐  Create project folder and initialise GitHub repo

☐  Get a blank window running in your engine

☐  Divide tasks — who codes what, who handles assets

## Ongoing Throughout

☐  Commit to GitHub at least every 2–3 hours

☐  Communicate blockers immediately — don’t get stuck silently

☐  Playtest regularly — is it actually fun?

☐  Cut features ruthlessly if you are behind schedule

☐  Take breaks and sleep — fatigue kills productivity and code quality

## Final 6 Hours

☐  Stop adding features — polish only from here

☐  Fix critical bugs only

☐  Export build and test on a clean machine if possible

☐  Write the itch.io description — what is it? what are the controls?

☐  Credit all external assets used in the description

☐  Submit before the deadline — don’t cut it too close!

# 8.  Key Rules Summary

| Rule | Detail |
| --- | --- |
| AI Art / Audio | BANNED — will result in disqualification |
| AI for Code | Discouraged but not enforced — use with integrity |
| Pre-made Assets | Allowed — must be credited in itch.io description |
| Pre-made Code | Allowed — libraries and boilerplate are fine |
| Content Rating | General audience only — no gore, nudity, or hate speech |
| Submission | Only one person needs to submit on itch.io |

# 9.  Free Asset Sources

| Category | Source | License |
| --- | --- | --- |
| Sprites & Art | Kenney.nl | CC0 — no credit needed |
| Sprites & Art | OpenGameArt.org | Varies — check per asset |
| Sprites & Art | itch.io/assets | Varies — check per asset |
| Sound Effects | freesound.org | Varies — check per asset |
| Sound Effects | Kenney.nl | CC0 — no credit needed |
| Music | incompetech.com | CC BY — credit required |
| Music | Pixabay | Free — no credit needed |
| Fonts | Google Fonts | Open Font License — free |

Tip: CC0 = completely free, no strings attached. CC BY = free but you must credit the creator.

# 10.  Notes During Jam

Use this space for decisions, ideas, or anything you need to remember.

Good luck! Ship something fun. 🎮